## Sheet1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#9 | Inspection form submission after rental for users | Define Requirements and identify necessary inspection report fields and data requirements and include them in the UI. Send the form upon submission to the DB | 1 | LOW | Possible risks for Inspection form submission after rental include miscommunication of requirements leading to UI inconsistencies, potential data mismatch in the inspection report, and database submission errors impacting data accuracy and refund/penalty calculations. | Armin | 2
#10 | Build API endpoint for refund or penalty | Identify the necessary parameters for refund or penalty requests Determine the conditions for issuing refunds or penalties Update the database schema to support refund and penalty data Create API endpoints to handle refund and penalty requests Integrate refund and penalty API with the rental system | 3 | HIGH-Changes in rental system API | Possible risks for Building API endpoint for refund or penalty include challenges in adapting to changes in the rental system API, potential discrepancies in identified parameters, and system integration issues leading to functionality gaps. | Mahad | 2
#11 | Connect buttons to endpoint | Identify the buttons requiring connection to an endpoint Develop code to handle button clicks and trigger API requests Retrieve the endpoint URL and ensure it aligns with the button action | 2 | MEDIUM-Integration issues | Possible risks for Connecting buttons to endpoint include potential integration issues due to discrepancies between identified buttons and actual API endpoints, leading to functional inconsistencies and user experience challenges. | Ardian | 2
#12 | Main page search and filtering companies and cars | Identify and design search and filtering elements on the main page for companies and cars Implement frontend components for search and filtering functionality Create backend API endpoints to support search and filtering requests Develop logic to retrieve and display relevant data based on search and filter criteria Implement sorting options for companies and cars based on various criteria | 3 | MEDIUM - Changes in cancellation policy | Possible risks for Main page search and filtering companies and cars include challenges in adapting to changes in the cancellation policy, potential discrepancies in identified search and filter criteria, and integration issues affecting data retrieval and display. | Omare | 2
#13 | ENDPOINT for Cancellation | Identify the parameters and conditions for cancellation requests Update the database schema to support cancellation data Create API endpoints to handle cancellation requests | 2 | HIGH-Security vulnerabilities | Possible risks for creating the ENDPOINT for Cancellation include potential security vulnerabilities due to improper handling of cancellation requests, challenges in identifying and validating parameters, and potential database schema vulnerabilities that may arise during the update process. | Mahad | 2
#14 | Rate form submission | Identify the required fields and criteria for submitting ratings Update the database schema to store rating data Create API endpoints for submitting ratings | 2 | LOW-Integration issues |  | Souleymane | 2
#15 | Database implementation for users | Identify the user data to be stored in the database (e.g., username, email, password, etc.) Design the database schema for storing user data Create the necessary tables and relationships for the user data in the database | 3 | HIGH-Integration issues | Possible risks for Database implementation for users include potential integration issues during the identification and design of user data, challenges in designing a robust database schema, and issues arising during the creation of tables and relationships, impacting overall system integration. | Armin | 2
#16 | Admin accounts page with user list | Design the admin accounts page layout and user list display Implement frontend components for displaying the user list on the admin accounts page Create backend API endpoint to retrieve and provide user data for the admin accounts page Develop logic to retrieve and display user data on the admin accounts page | 3 | HIGH-Changes in company information structure | Possible risks for Admin accounts page with user list include challenges in adapting to changes in the company information structure, potential discrepancies in the design and implementation of the admin accounts page, and integration issues affecting the retrieval and display of user data. Changes in the company information structure might impact the overall design and functionality of the admin accounts page. | Souleymane | 2-3
#17 | My bookings page for users | Implement frontend components for displaying user bookings on the My Bookings page Create a backend API endpoint to retrieve and provide user booking data Develop logic to retrieve and display user booking data on the My Bookings page Implement detailed view of each booking with relevant information | 3 | HIGH-Security vulnerabilities | Possible risks for My bookings page for users include potential security vulnerabilities during the implementation of frontend components, challenges in creating a secure backend API endpoint for retrieving booking data, and issues related to security in the development of detailed views for each booking. Ensuring robust security measures is crucial to mitigate potential vulnerabilities. | Ardian | 2-3
#18 | Confirmation page | Design the layout and components for the confirmation page Implement frontend components for displaying booking confirmation details Show relevant details such as booking ID, dates, and payment information on the confirmation page Implement an option for users to download or print the booking confirmation | 2 | MEDIUM-Integration issues | Possible risks for Confirmation page include potential integration issues during the design and implementation of layout and components, challenges in displaying accurate booking confirmation details on the frontend, and potential complications in providing the option for users to download or print the booking confirmation due to integration challenges. Ensuring smooth integration is crucial to avoid functionality gaps. | Omare | 2
#19 | Send email endpoint | Identify the content and parameters required for the email (e.g., recipient, subject, body) Design the layout and structure of the email template Develop the backend logic for sending emails using an email service or API | 2 | MEDIUM-Security vulnerabilities | Possible risks for Send email endpoint include potential security vulnerabilities during the identification and design of email content and parameters, challenges in designing a secure email template layout and structure, and issues related to security in the development of backend logic for sending emails using an email service or API. Implementing robust security measures is essential to mitigate potential vulnerabilities. | Souleymane | 2
#20 | Log In/ Sign up popup modal | Implement frontend components for the popup modal with separate sections for Log In and Sign Up Connect the modal to backend authentication services for user authentication and registration Implement validation checks for user input (e.g., email format, password strength Develop functionality to toggle between Log In and Sign Up sections within the popup modal | 3 | HIGH-Security vulnerabilities | Possible risks for Log In/Sign Up popup modal include potential security vulnerabilities during the implementation of frontend components, challenges in connecting the modal to secure backend authentication services, issues related to validation checks for user input, and potential security vulnerabilities in the development of functionality to toggle between Log In and Sign Up sections. Ensuring strong security measures is crucial to mitigate potential vulnerabilities. | Ardian | 2
#21 | Database implementation for companies | Identify the data to be stored for each company (e.g., company name, location, contact information) Design the database schema for storing company data Create the necessary tables and relationships for the company data in the database Create API endpoint for updating company information in the database | 3 | HIGH-Changes in company information structure | Possible risks for Database implementation for companies include challenges in adapting to changes in the company information structure during the identification and design of company data, potential discrepancies in the design of the database schema, issues during the creation of tables and relationships, and potential complications in creating a stable API endpoint for updating company information due to changes in the company information structure. Adapting to changes in the structure is crucial to maintaining database functionality. | Mahad | 2-3